## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
Context Diagrams | Identify Human Resources Areas | Shawn | Closed | 7 | 5 | 3 | 4 | 0 | 0
| Identify Human Resources Relationships | Shawn | Closed | 7 | 6 | 5 | 4 | 0.5 | 0
| Identify Customer Relations Areas | Ben | Closed | 7 | 3 | 4 | 1 | 1 | 2
| Identify Customer Relations Relationships | Ben | Closed | 7 | 7 | 5 | 0 | 0 | 0
| Identify Inventory Areas | Ben/Shawn | Closed | 5 | 3 | 5 | 3 | 2 | 0
| Identify Inventory Relationships | Ben/Shawn | Closed | 7 | 3 | 6 | 1 | 1 | 2
Use Case Diagrams | Identify Human Resources Actors | Shawn | Closed | 6 | 6 | 5 | 1 | 1 | 0
| Identify Human Resources Use Cases | Shawn | Closed | 6 | 5 | 5 | 3 | 0 | 0
| Identify Human Resources Relationships | Shawn | Closed | 8 | 7 | 6 | 0.5 | 0.5 | 0
| Identify Customer Relations Actors | Ben | Closed | 5 | 1 | 4 | 4 | 1 | 0
| Identify Customer Relations Use Cases | Ben | Closed | 5 | 0 | 4 | 5 | 0 | 0
| Identify Customer Relations Relationships | Ben | Closed | 5 | 3 | 4 | 4 | 0 | 0
| Identify Inventory Actors | Ben/Shawn | Closed | 5 | 1 | 4 | 1 | 1 | 2
| Identify Inventory Use Cases | Ben/Shawn | Closed | 4 | 3 | 4 | 3 | 0 | 0
| Identify Inventory Relationships | Ben/Shawn | Closed | 6 | 5 | 5 | 3 | 0.5 | 0
Fishbone Diagram | Determine Project Categories | Ben/Shawn | Closed | 7 | 5 | 5 | 5 | 1 | 0
| Identify Equipment Issues | Ben/Shawn | Closed | 8 | 7 | 5 | 2 | 0 | 0
| Identify Process Issues | Ben/Shawn | Closed | 7 | 5 | 6 | 2 | 0 | 0
| Identify People Issues | Ben/Shawn | Closed | 8 | 6 | 6 | 3 | 1 | 1
| Identify Training Issues | Ben/Shawn | Closed | 8 | 6 | 7 | 4 | 2 | 2
| Identify Policy/Procedure Issues | Ben/Shawn | Closed | 9 | 7 | 6 | 5 | 1 | 2
| Identify Material Issues | Ben/Shawn | Closed | 8 | 6 | 6 | 3 | 1 | 2
| Identify Environment Issues | Ben/Shawn | Closed | 8 | 6 | 7 | 4 | 1 | 2
| Identify Management Issues | Ben/Shawn | Closed | 7 | 5 | 5 | 2 | 0 | 2
| Identify Data Issues | Ben/Shawn | Closed | 9 | 7 | 5 | 1 | 0 | 2
| Identify Time/Scheduling Issues | Ben/Shawn | Closed | 7 | 5 | 6 | 4 | 0 | 0
Problem Matrix | Identify Main Problems | Ben/Shawn | Closed | 6 | 3 | 4 | 2 | 0 | 0
| Identify Impact of Issues | Ben/Shawn | Closed | 6 | 5 | 5 | 1 | 0 | 0
| Identify Urgency & Frequency | Ben/Shawn | Closed | 8 | 5 | 4 | 2 | 0 | 0
| Identify Difficulty to Fix | Ben/Shawn | Closed | 7 | 6 | 5 | 2 | 0 | 0
| Identify Priority & Total score | Ben/Shawn | Closed | 5 | 3 | 3 | 1 | 0 | 0
| Recommend Solutions | Ben/Shawn | Closed | 5 | 4 | 3 | 2 | 1 | 2
Decomposition Diagrams | Identify Human Resource Heirarchical Levels | Shawn | Closed | 6 | 5 | 4 | 3 | 0 | 0
| Identify Customer Relations Hierarchical Levels | Ben | Closed | 5 | 4 | 3 | 2 | 0 | 0
| Identify Inventory Hierarchical Levels | Ben/Shawn | Closed | 6 | 5 | 3 | 2 | 0 | 0
| Total | 687 | (Closed/Open/In Progress) | 230 | 163 | 167 | 89.5 | 16.5 | 21
Sprint Goal
Cuzzie Movers Information System
Our goal is to complete our tasks and ensure each one is eventually closed. Ensuring we get what we need done so everything is in order and/or presentable for our Cuzzie Movers Information System.